## Slide 1
WORKSHOP PRESENTATION
Estimation of User Stories, Yesterday's Weather
Relative sizing, honest forecasting, and using what we actually did
ScrumMaster Hub · scrummaster-hub.vercel.app/workshops

## Slide 2
OBJECTIVES
By the end of this session you will be able to…
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
2 / 16
Explain why we estimate — and what estimates are and are not for
Size stories relatively using story points and reference stories
Run a planning poker round and use disagreement productively
Apply 'Yesterday's Weather' to set a realistic Sprint capacity
Recognise when estimation effort stops paying for itself

## Slide 3
ICE BREAKER
Ice breaker — pick one
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
3 / 16
Option A · 8 min · Guess the jar
Show a jar of sweets (or a picture). Everyone writes an individual guess of the count
Calculate the group average and compare with the real count
Discuss: was the group closer than most individuals?
Link to planning poker: many independent views beat one loud one
Option B · 8 min · Size things relatively
Give cards: mouse, cat, dog, horse, elephant
Order them from smallest to biggest without measuring
Then ask: how many times bigger is the dog than the cat?
Notice how easy relative comparison is, and how hard exact numbers are
Debrief: The same instinct underlies story points: we are far better at comparing sizes than at predicting exact durations.

## Slide 4
CONCEPT
Why we estimate at all
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
4 / 16
To forecast: roughly how much can we take on, and when might this be done?
To start a conversation: differing numbers reveal hidden assumptions and risks
To help the Product Owner make trade-offs between value and cost
Estimates are forecasts, not promises — accuracy has limits, especially early on
The conversation is often worth more than the number
If estimating does not change a decision or reveal a risk, we are probably over-investing in it.

## Slide 5
CONCEPT
Absolute vs. relative estimation
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
5 / 16
Absolute (hours, days)
'This will take 3 days' — feels precise
Depends heavily on who does the work
Easy to turn into a commitment or a deadline
People are consistently over-optimistic
Relative (story points)
'This is about twice as big as that one'
Compares effort, complexity and uncertainty together
Independent of individual speed — the team estimates
Faster, and quality of discussion improves

## Slide 6
CONCEPT
Story points and reference stories
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
6 / 16
Points measure relative size: effort, complexity and uncertainty combined — not hours
A common scale is 1, 2, 3, 5, 8, 13 — gaps grow because larger items are less certain
Choose one or two reference stories the team knows well (for example, a '3' and a '5')
Compare each new story to references: 'is it bigger or smaller than our 5?'
Very large items (13 and above) are usually a signal to slice the story
Points belong to one team. Never compare one team's points with another's.

## Slide 7
CONCEPT
Planning poker in six steps
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
7 / 16
1
Product Owner explains the story
A short description and the acceptance criteria.
2
Team asks questions
Clarify scope and unknowns before anyone estimates.
3
Everyone picks a card privately
So nobody is anchored by a senior voice.
4
Reveal together
Cards turned at the same time.
5
Discuss the highest and lowest
The outliers explain their reasoning — often a missed assumption.
6
Re-vote until the estimates converge
Or split the story if the disagreement is about scope.
Technique described by James Grenning (2002) and popularised by Mike Cohn.

## Slide 8
CONCEPT
Yesterday's Weather
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
8 / 16
An Extreme Programming idea: the best predictor of what we can do next Sprint is what we actually did recently
Look at completed work (Done items only) from the last 3–6 Sprints
Use the average as a starting point and the min–max as the honest range
Adjust for known changes: holidays, leave, new joiners, planned support duty
It replaces optimistic re-estimation each Sprint with evidence
Named after weather forecasting: 'tomorrow will most likely be like today.'

## Slide 9
CONCEPT
Estimates get better as we learn
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
9 / 16
The 'cone of uncertainty' (Barry Boehm): early estimates can be far off, and the range narrows as work progresses
So give ranges early and refine them as unknowns are resolved
Slicing and spikes reduce uncertainty; more meetings do not
Alternatives exist: count items completed per week, or use cycle-time forecasts (see the metrics articles)
Choose the lightest approach that still supports our decisions

## Slide 10
LIVE EXAMPLE
Live example: Yesterday's Weather in numbers
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
10 / 16
Step | Calculation | Result
Last three Sprints (Done points) | 21, 18, 24 | Average = (21 + 18 + 24) ÷ 3 = 21
Honest range from history | Lowest 18, highest 24 | 18–24 points
Adjust: two of ten people on leave (20%) | 21 × 0.8 = 16.8; 18 × 0.8 = 14.4; 24 × 0.8 = 19.2 | Plan about 17 (range 14–19)
Plan the Sprint | Pull items until roughly 17 points, leave slack for the unexpected | Sprint Goal first, extras after
Illustrative numbers. Yesterday's Weather gives a starting point — the team still decides what it can commit to.

## Slide 11
LIVE EXAMPLE
Live example: an outlier that saved the Sprint
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
11 / 16
1
Story
'Show order history on the profile page.'
2
First reveal
Estimates: 3, 3, 5 and 13.
3
Outlier explains
The 13 says: 'Order data is in the old system — it needs a data migration nobody mentioned.'
4
New information
The team splits it: read from the new system now (3), plan migration separately.
5
Second reveal
Estimates converge on 3, and the migration becomes its own backlog item with a proper estimate.
Illustrative scenario. The value of the round was the disagreement, not the average.

## Slide 12
REAL-LIFE USE
Using estimates in real life
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
12 / 16
Sprint Planning: use Yesterday's Weather to check the forecast against a realistic capacity
Release forecasting: 120 points remaining ÷ 21 average ≈ 5.7 Sprints; with 18–24 that is roughly 5–7 Sprints
Communicating with stakeholders: give a range and what would change it, not a single date
Capacity for holidays and support duty: scale the average by available people
Deciding when to stop estimating: if items are similar size, counting them may be enough

## Slide 13
WATCH OUT
Estimation traps
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
13 / 16
Converting points into hours — this undoes the reason for using points
Comparing velocities between teams, or pushing a team to 'improve' its points
False precision: arguing whether a story is 5 or 8 for ten minutes
Re-estimating finished work to make the numbers look better
Treating estimates as commitments and punishing variance

## Slide 14
TRY IT
Try it: estimate real items and apply Yesterday's Weather
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
14 / 16
1
Choose reference stories (10 min)
Agree one 'small' and one 'medium' story from our past work.
2
Estimate 5–6 upcoming items (25 min)
Planning poker; write down each discussion outlier's reason.
3
Calculate Yesterday's Weather (10 min)
Use our last 3 Sprints; adjust for planned leave; note the range.
4
Reflect (5 min)
Which items should be sliced or investigated before Sprint Planning?

## Slide 15
TAKEAWAYS
Key takeaways
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
15 / 16
Estimates are forecasts that start a conversation — not promises
Relative sizing with reference stories is quicker and often more reliable than hours
Yesterday's Weather uses what we really delivered, as a range, adjusted for known changes
Stop investing when extra estimating stops changing decisions

## Slide 16
GO DEEPER
Go deeper: sources worth your time
ScrumMaster Hub · Estimation of User Stories, Yesterday's Weather
16 / 16
Agile Estimating and Planning — Mike Cohn BOOK
The standard reference on story points, planning poker and velocity.
Extreme Programming Explained — Kent Beck BOOK
The origin of Yesterday's Weather and other planning ideas in XP.
Planning Poker or How to Avoid Analysis Paralysis while Release Planning — James Grenning (2002) ARTICLE
The original planning poker write-up.
When Will It Be Done? — Daniel Vacanti BOOK
Probabilistic forecasting from historical flow data — an alternative to estimates.
Software Estimation: Demystifying the Black Art — Steve McConnell BOOK
Why estimates are uncertain, the cone of uncertainty and how to give ranges.