## Slide 1
WORKSHOP PRESENTATION
Velocity and Its Importance to the Team
A forecasting tool for the team — not a performance score
ScrumMaster Hub · scrummaster-hub.vercel.app/workshops

## Slide 2
OBJECTIVES
By the end of this session you will be able to…
ScrumMaster Hub · Velocity and Its Importance to the Team
2 / 15
Define velocity precisely and calculate it from Done work
Use velocity as a range to forecast Sprints and release dates
Explain what influences velocity and how to read a trend
Explain why targets and cross-team comparisons backfire (Goodhart's law)
Agree our team's ground rules for how velocity will and will not be used

## Slide 3
ICE BREAKER
Ice breaker — pick one
ScrumMaster Hub · Velocity and Its Importance to the Team
3 / 15
Option A · 6 min · Commute-time forecast
Everyone writes down their commute (or a routine trip) for the last five days
Compute the average and the fastest/slowest
Ask: what time would you tell a friend to expect you — one number or a range?
Link to velocity: recent history gives a range, not a promise
Option B · 6 min · Steps-per-day guess
Each person estimates how many steps they will walk tomorrow
Compare with what their recent days actually looked like
Discuss: is yesterday a better predictor than optimism?
Link to Yesterday's Weather and velocity
Debrief: Both games use the same logic as velocity: recent actuals beat wishful thinking as a forecast.

## Slide 4
CONCEPT
What velocity is — and how it is calculated
ScrumMaster Hub · Velocity and Its Importance to the Team
4 / 15
The amount of work (usually story points) a team completes in a Sprint
Count only items that are fully Done — no partial credit for started work
Specific to one team's own estimating scale; points are not a universal unit
Plot it over time and look at the range, not just the last number
It describes the past; it is not a target for the future
Velocity = sum of points of items that met the Definition of Done in the Sprint.

## Slide 5
CONCEPT
What velocity is for
ScrumMaster Hub · Velocity and Its Importance to the Team
5 / 15
Good uses
Forecasting how much we can take into the next Sprint
Forecasting a release: remaining points ÷ velocity
Spotting trends: something changed in how we work
Conversations about capacity, leave and interruptions
Misuses
A target ('increase by 10% next quarter')
Comparing teams or ranking them
Judging individuals
Reporting it to executives as productivity

## Slide 6
CONCEPT
What moves velocity
ScrumMaster Hub · Velocity and Its Importance to the Team
6 / 15
Factor | How it shows up
Team changes (people join, leave, leave on holiday) | Available capacity rises or falls
Unplanned work (incidents, support) | Fewer planned items finish
Technical debt and quality issues | Work slows and rework grows
Estimation drift | Points quietly inflate or deflate over time
Story size and clarity | Big, unclear items finish late or partially

## Slide 7
CONCEPT
Reading a velocity trend
ScrumMaster Hub · Velocity and Its Importance to the Team
7 / 15
Pattern | Possible meaning | What to ask
Stable within a range | Predictable delivery | Can we use the range for forecasting?
Steadily rising | Real improvement — or point inflation | Did cycle time or stories completed change too?
Sudden drop | Absence, incident, tech debt, or new people | What changed this Sprint?
Volatile | Large or unclear stories; interruptions | Can we slice smaller and protect focus?

## Slide 8
CONCEPT
Goodhart's law: when the measure becomes the target
ScrumMaster Hub · Velocity and Its Importance to the Team
8 / 15
'When a measure becomes a target, it ceases to be a good measure' — the idea usually credited to Charles Goodhart
If velocity is rewarded, people adjust points, not delivery
Points inflate; conversations about real value fade; trust in the number is lost
Pair velocity with outcome measures: cycle time, quality, customer feedback
Ask 'what decision does this number support?' before reporting it
Protect velocity by keeping it inside the team and only for forecasting.

## Slide 9
LIVE EXAMPLE
Live example: forecasting a release from history
ScrumMaster Hub · Velocity and Its Importance to the Team
9 / 15
Done points, last six Sprints
Sprint 1: 18 · Sprint 2: 22 · Sprint 3: 20
Sprint 4: 25 · Sprint 5: 19 · Sprint 6: 21
Average of all six ≈ 20.8; average of the last three ≈ 21.7
Lowest 18, highest 25 — this is our honest range
Forecast: 130 points remaining
Best case: 130 ÷ 25 ≈ 5.2 Sprints
Likely: 130 ÷ 21 ≈ 6.2 Sprints
Cautious: 130 ÷ 18 ≈ 7.2 Sprints
Round up, since only whole Sprints exist on the calendar
Share with stakeholders: 'most likely 6–7 Sprints; 5–6 if all goes well; 7–8 if it does not.'
Notes: Illustrative numbers. Always give the range and what would move it, never a single date.

## Slide 10
LIVE EXAMPLE
Live example: when a target inflated the number
ScrumMaster Hub · Velocity and Its Importance to the Team
10 / 15
Measure | Before target | After target ('+20%')
Velocity (points per Sprint) | 20 | 24
Stories completed per Sprint | 7 | 7
Average cycle time per story | 5 days | 5 days
What people actually received | 7 finished stories per Sprint | 7 finished stories per Sprint
Illustrative scenario. The number rose 20% but delivery did not change: the team re-sized its stories.

## Slide 11
REAL-LIFE USE
Using velocity well in real life
ScrumMaster Hub · Velocity and Its Importance to the Team
11 / 15
Sprint Planning: compare the plan against the range from the last 3–6 Sprints
Release conversations: give a range and what would change it, not one date
Leave and holidays: scale expected capacity by people available
When leadership asks for velocity comparisons: explain points are team-specific and offer outcome measures instead
Retrospectives: use a drop or rise as a question, not a verdict

## Slide 12
WATCH OUT
How velocity gets misused
ScrumMaster Hub · Velocity and Its Importance to the Team
12 / 15
Setting a velocity target or celebrating an increase
Comparing velocities across teams or showing them side by side
Counting partially finished work
Changing the estimation scale mid-way and comparing before and after
Reporting velocity outside the team without context

## Slide 13
TRY IT
Try it: forecast and agree our ground rules
ScrumMaster Hub · Velocity and Its Importance to the Team
13 / 15
1
Chart our last 6 Sprints (10 min)
Plot Done points; note anything unusual for each Sprint.
2
Compute range and forecast (10 min)
Average, min, max; divide the remaining backlog by each.
3
Discuss the trend (10 min)
Is it stable, rising or volatile? What is behind it?
4
Agree ground rules (10 min)
Velocity stays in the team, is never a target, and is never used to compare teams.
5
Prepare a shared reply (5 min)
What we say if someone asks to compare velocity across teams.

## Slide 14
TAKEAWAYS
Key takeaways
ScrumMaster Hub · Velocity and Its Importance to the Team
14 / 15
Velocity is Done points per Sprint, specific to one team, and useful for forecasting ranges
Read trends as questions: what changed?
Targets and comparisons make the number meaningless (Goodhart's law)
Agree ground rules and pair velocity with outcome measures

## Slide 15
GO DEEPER
Go deeper: sources worth your time
ScrumMaster Hub · Velocity and Its Importance to the Team
15 / 15
Agile Estimating and Planning — Mike Cohn BOOK
The standard treatment of velocity and release forecasting.
Actionable Agile Metrics for Predictability — Daniel Vacanti BOOK
Flow metrics as an alternative to points-based velocity.
The Velocity Conversation — ScrumMaster Hub ARTICLE
How to respond when leadership asks why velocity has not gone up. https://scrummaster-hub.vercel.app/resources/articles/metrics/velocity-conversation-with-leadership
The Scrum Guide — forecasting in Sprint Planning — Ken Schwaber & Jeff Sutherland GUIDE
How the team forecasts what it can complete. https://scrumguides.org
Goodhart's law — Charles Goodhart; phrased by Marilyn Strathern RESEARCH
The origin of 'when a measure becomes a target, it ceases to be a good measure'.